## Instructions
FYS.330 Project Work — Gantt chart workbook
This workbook is the editable companion to the Gantt chart (Table 2.2) in the LaTeX project plan template. Edit it here, then e.g. send the file to Claude and ask to update the LaTeX chart to match.
How the three sheets fit together
• Weeks — the calendar spine for the whole course (week 43/2026 to week 18/2027). Each row is one real calendar week: its dates, which phase it belongs to (Planning / Implementation / Reporting), and whether it's a break. The Project Week number is computed automatically — it just counts the non-break rows in order.
• Tasks — the master task/deliverable list (mirrors Table 2.1 in the LaTeX document). Each row has a Start and End given as a Calendar Week (matching the 'Calendar Week' column on the Weeks sheet) — this is what you edit. The Project Week columns and the date columns to their right are computed automatically from the Weeks sheet.
• Gantt — an automatic visual preview, built entirely from formulas reading the two sheets above. You don't edit this sheet directly — change Tasks or Weeks and this sheet updates itself.
What to edit
• Blue text = a cell you're meant to edit.
• Black text = a formula — leave it alone, it recalculates on its own.
• To move a task: change its Start/End Calendar Week on the Tasks sheet.
• To add a task or deliverable: add a new row on the Tasks sheet, following the same columns and using a Calendar Week that already exists on the Weeks sheet; the Gantt sheet picks it up automatically (extend its row range if you add rows beyond D5).
• To move a break, or change which weeks belong to which phase: edit the Phase / Is Break / Break Label columns on the Weeks sheet. Project Week numbers renumber automatically.
This workbook mirrors the example schedule already in the LaTeX template (main.tex / Chapters/ChapII_Implementation.tex) as of the last edit.

## Weeks
Calendar Week | Week Start | Week End | Phase | Is Break (Y/N) | Break Label | Project Week
W43/2026 | 2026-10-19 | 2026-10-25 | Planning | N |  | 1
W44/2026 | 2026-10-26 | 2026-11-01 | Planning | N |  | 2
W45/2026 | 2026-11-02 | 2026-11-08 | Planning | N |  | 3
W46/2026 | 2026-11-09 | 2026-11-15 | Planning | N |  | 4
W47/2026 | 2026-11-16 | 2026-11-22 | Planning | N |  | 5
W48/2026 | 2026-11-23 | 2026-11-29 | Planning | N |  | 6
W49/2026 | 2026-11-30 | 2026-12-06 | Planning | N |  | 7
W50/2026 | 2026-12-07 | 2026-12-13 | Break | Y | Christmas break
W51/2026 | 2026-12-14 | 2026-12-20 | Break | Y | Christmas break
W52/2026 | 2026-12-21 | 2026-12-27 | Break | Y | Christmas break
W01/2027 | 2027-01-04 | 2027-01-10 | Break | Y | Christmas break
W02/2027 | 2027-01-11 | 2027-01-17 | Implementation | N |  | 8
W03/2027 | 2027-01-18 | 2027-01-24 | Implementation | N |  | 9
W04/2027 | 2027-01-25 | 2027-01-31 | Implementation | N |  | 10
W05/2027 | 2027-02-01 | 2027-02-07 | Implementation | N |  | 11
W06/2027 | 2027-02-08 | 2027-02-14 | Implementation | N |  | 12
W07/2027 | 2027-02-15 | 2027-02-21 | Implementation | N |  | 13
W08/2027 | 2027-02-22 | 2027-02-28 | Break | Y | Exam week
W09/2027 | 2027-03-01 | 2027-03-07 | Reporting | N |  | 14
W10/2027 | 2027-03-08 | 2027-03-14 | Reporting | N |  | 15
W11/2027 | 2027-03-15 | 2027-03-21 | Reporting | N |  | 16
W12/2027 | 2027-03-22 | 2027-03-28 | Reporting | N |  | 17
W13/2027 | 2027-03-29 | 2027-04-04 | Reporting | N |  | 18
W14/2027 | 2027-04-05 | 2027-04-11 | Reporting | N |  | 19
W15/2027 | 2027-04-12 | 2027-04-18 | Reporting | N |  | 20
W16/2027 | 2027-04-19 | 2027-04-25 | Reporting | N |  | 21
W17/2027 | 2027-04-26 | 2027-05-02 | Break | Y | Exam period
W18/2027 | 2027-05-03 | 2027-05-09 | Break | Y | Exam period

## Tasks
ID | Task | Responsible | Type | Start (Cal Wk) | End (Cal Wk) | Deliverable / Milestone | Start Date | End Date | Start (Proj Wk) | End (Proj Wk) | Gantt label
T1 | Kickoff and background research | Whole team | Task | W43/2026 | W44/2026 | Shared reading list | 2026-10-19 | 2026-11-01 | 1 | 2 | Kickoff & background research
T2 | Detailed literature review | Author A | Task | W44/2026 | W47/2026 | Background chapter draft | 2026-10-26 | 2026-11-22 | 2 | 5 | Literature review
D1 | Return of preliminary project plan | Whole team | Deliverable | W47/2026 | W47/2026 | DL Sun 22.11 23:59 | 2026-11-16 | 2026-11-22 | 5 | 5 | Prelim. plan due
T3 | Method / experimental design | Author B | Task | W47/2026 | W49/2026 | Method description | 2026-11-16 | 2026-12-06 | 5 | 7 | Method/experimental design
D2 | Return of final project plan | Whole team | Deliverable | W49/2026 | W49/2026 | DL Fri 4.12 23:59 | 2026-11-30 | 2026-12-06 | 7 | 7 | Final plan due
T4 | Data collection / simulations | Whole team | Task | W02/2027 | W05/2027 | Raw data set | 2027-01-11 | 2027-02-07 | 8 | 11 | Data collection / simulations
T5 | Interim review meeting | Whole team | Milestone | W04/2027 | W04/2027 | Meeting notes (milestone) | 2027-01-25 | 2027-01-31 | 10 | 10 | Interim review
T6 | Data analysis | Author C | Task | W06/2027 | W07/2027 | Analysis notebook / results | 2027-02-08 | 2027-02-21 | 12 | 13 | Data analysis
T7 | Draft report writing | Whole team | Task | W09/2027 | W11/2027 | Full draft report | 2027-03-01 | 2027-03-21 | 14 | 16 | Draft report writing
D3 | Return of implementation report | Whole team | Deliverable | W11/2027 | W11/2027 | DL Sun 21.3 23:59 | 2027-03-15 | 2027-03-21 | 16 | 16 | Impl. report due
T8 | Prepare presentation | Whole team | Task | W12/2027 | W14/2027 | Full draft report | 2027-03-22 | 2027-04-11 | 17 | 19 | Prepare presentation
T9 | Final report and presentation | Whole team | Milestone | W14/2027 | W16/2027 | Final report, slides | 2027-04-05 | 2027-04-25 | 19 | 21 | Final report & presentation
D4 | Return of project presentation | Whole team | Deliverable | W16/2027 | W16/2027 | DL Sun 25.4 23:59 | 2027-04-19 | 2027-04-25 | 21 | 21 | Presentation due
D1 | Return of preliminary project plan | Whole team | Deliverable | W47/2026 | W47/2026 | DL Sun 22.11 23:59 | 2026-11-16 | 2026-11-22 | 5 | 5 | Prelim. plan due
D2 | Return of final project plan | Whole team | Deliverable | W49/2026 | W49/2026 | DL Fri 4.12 23:59 | 2026-11-30 | 2026-12-06 | 7 | 7 | Final plan due
D3 | Return of implementation report | Whole team | Deliverable | W11/2027 | W11/2027 | DL Sun 21.3 23:59 | 2027-03-15 | 2027-03-21 | 16 | 16 | Impl. report due
D4 | Return of project presentation | Whole team | Deliverable | W16/2027 | W16/2027 | DL Sun 25.4 23:59 | 2027-04-19 | 2027-04-25 | 21 | 21 | Presentation due
D5 | Return of personal course reflection | Individual | Deliverable | W18/2027 | W18/2027 | DL Sun 9.5 23:59 (exam period) | 2027-05-03 | 2027-05-09 |  |  | Reflection due

## Gantt
ID | Task (Responsible) | W43/2026 | W44/2026 | W45/2026 | W46/2026 | W47/2026 | W48/2026 | W49/2026 | W50/2026 | W51/2026 | W52/2026 | W01/2027 | W02/2027 | W03/2027 | W04/2027 | W05/2027 | W06/2027 | W07/2027 | W08/2027 | W09/2027 | W10/2027 | W11/2027 | W12/2027 | W13/2027 | W14/2027 | W15/2027 | W16/2027 | W17/2027 | W18/2027
| Project week -> | 1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  |  |  | 8 | 9 | 10 | 11 | 12 | 13 |  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
| Week start (helper) -> | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03
T1 | Kickoff and background research (Whole team) | 1 | 2 | [26 empty] | 2026-10-19 | 2026-11-01 | Task
T2 | Detailed literature review (Author A) |  | 2 | 3 | 4 | 5 | [23 empty] | 2026-10-26 | 2026-11-22 | Task
D1 | Return of preliminary project plan (Whole team) |  |  |  |  | D1 | [23 empty] | 2026-11-16 | 2026-11-22 | Deliverable
T3 | Method / experimental design (Author B) |  |  |  |  | 5 | 6 | 7 | [21 empty] | 2026-11-16 | 2026-12-06 | Task
D2 | Return of final project plan (Whole team) | [6 empty] | D2 | [21 empty] | 2026-11-30 | 2026-12-06 | Deliverable
T4 | Data collection / simulations (Whole team) | [11 empty] | 8 | 9 | 10 | 11 | [13 empty] | 2027-01-11 | 2027-02-07 | Task
T5 | Interim review meeting (Whole team) | [13 empty] | 10 | [14 empty] | 2027-01-25 | 2027-01-31 | Milestone
T6 | Data analysis (Author C) | [15 empty] | 12 | 13 | [11 empty] | 2027-02-08 | 2027-02-21 | Task
T7 | Draft report writing (Whole team) | [18 empty] | 14: 14; 15: 15; 16: 16 |  |  | 2027-03-01 | 2027-03-21 | Task
D3 | Return of implementation report (Whole team) | [28 empty] | 2027-03-15 | 2027-03-21 | Deliverable | bar: 16
T8 | Prepare presentation (Whole team) | [18 empty] | 17: 17; 18: 18; 19: 19 |  |  | 2027-03-22 | 2027-04-11 | Task
T9 | Final report and presentation (Whole team) | [18 empty] | 19: 19; 20: 20; 21: 21 |  |  | 2027-04-05 | 2027-04-25 | Milestone
D4 | Return of project presentation (Whole team) | [28 empty] | 2027-04-19 | 2027-04-25 | Deliverable | bar: 21